## Estimation
Client | adf.ly
Project | adf.ly iOS and Android app
Date | 28/04/2015
Version | 1
Assumptions | Application will support all languages supported by the website
Application will support all languages supported by the website
Application will support both portrait and landscape mode
Application will web-services for data communication with the web-site, provided by the client
The estimate is subject to change if and when new information is received or the final designs are approved
| Task | Min Hours | Max Hours | Rate | Min Cost | Max Cost
iOS Development
| PM | 20 | 30
| PM | 20 | 30
| iOS Application Development | 144 | 216
| Setting up the project | 8 | 16
| Home screen for fast shrink & info | 8 | 16
| Login and Signup | 12 | 18
| Login with Facebook | 6 | 8
| Forgotten password and terms of service | 4 | 8
| Statistics chart screen | 16 | 24
| Filters for statistics | 12 | 16
| Your links + searching and filtering | 12 | 16
| Profile screen | 8 | 12
| Referals screen | 10 | 14
| Withdraw screen | 10 | 14
| Support screen | 4 | 6
| Settings | 6 | 8
| Advertisers statistics | 12 | 16
| Advertisers filters | 8 | 12
| Announcements | 8 | 12
| Quality Assurance | 24 | 30
| QA | 24 | 30
| Deployment | 2 | 2
| Deployment to Apple AppStore | 2 | 2
| Revisions | 32 | 32
| Mobile Development | 24 | 24
| PM | 2 | 2
| QA | 6 | 6
Android Development
| PM | 20 | 30
| PM | 20 | 30
| Android Application Development | 174 | 262
| Setting up the project | 8 | 16
| Home screen for fast shrink & info | 8 | 16
| Login and Signup | 12 | 18
| Login with Facebook | 6 | 8
| Forgotten password and terms of service | 4 | 8
| Statistics chart screen | 16 | 24
| Filters for statistics | 12 | 16
| Your links + searching and filtering | 12 | 16
| Profile screen | 8 | 12
| Referals screen | 10 | 14
| Withdraw screen | 10 | 14
| Support screen | 4 | 6
| Settings | 6 | 8
| Advertisers statistics | 12 | 16
| Advertisers filters | 8 | 12
| Announcements | 8 | 12
| Getting to know the project | 8 | 16
| Home screen | 12 | 16
| Help screen | 10 | 14
| Quality Assurance | 24 | 30
| QA | 24 | 30
| Deployment | 2 | 2
| Deployment to Google Play | 2 | 2
| Revisions | 32 | 32
| Mobile Development | 24 | 24
| QA | 6 | 6
| PM | 2 | 2