## General
Client | adf.ly
Project | adf.ly iOS and Android app
Date | 28/04/2015
Version | 1
Assumptions | Application will support all languages supported by the website
Application will support all languages supported by the website
Application will support both portrait and landscape mode
Application will web-services for data communication with the web-site, provided by the client
The estimate is subject to change if and when new information is received or the final designs are approved

## iOS Development
Task | Min Hours | Max Hours | Rate | Min Cost | Max Cost
PM
PM | 20 | 30
iOS Application Development
Setting up the project | 8 | 16
Home screen for fast shrink & info | 8 | 16
Login and Signup | 12 | 18
Login with Facebook | 6 | 8
Forgotten password and terms of service | 4 | 8
Statistics chart screen | 16 | 24
Filters for statistics | 12 | 16
Your links + searching and filtering | 12 | 16
Profile screen | 8 | 12
Referals screen | 10 | 14
Withdraw screen | 10 | 14
Support screen | 4 | 6
Settings | 6 | 8
Advertisers statistics | 12 | 16
Advertisers filters | 8 | 12
Announcements | 8 | 12
Quality Assurance
QA | 24 | 30
Deployment
Deployment to Apple AppStore | 2 | 2
Revisions
Mobile Development | 24 | 24
PM | 2 | 2
QA | 6 | 6

## Android Development
Task | Min Hours | Max Hours | Rate | Min Cost | Max Cost
PM
PM | 20 | 30
Android Application Development
Setting up the project | 8 | 16
Home screen for fast shrink & info | 8 | 16
Login and Signup | 12 | 18
Login with Facebook | 6 | 8
Forgotten password and terms of service | 4 | 8
Statistics chart screen | 16 | 24
Filters for statistics | 12 | 16
Your links + searching and filtering | 12 | 16
Profile screen | 8 | 12
Referals screen | 10 | 14
Withdraw screen | 10 | 14
Support screen | 4 | 6
Settings | 6 | 8
Advertisers statistics | 12 | 16
Advertisers filters | 8 | 12
Announcements | 8 | 12
Getting to know the project | 8 | 16
Home screen | 12 | 16
Help screen | 10 | 14
Quality Assurance
QA | 24 | 30
Deployment
Deployment to Google Play | 2 | 2
Revisions
Mobile Development | 24 | 24
QA | 6 | 6
PM | 2 | 2